## Client
MSU Client Development Effort
MSU Clinet Activity | Effort in week
Product spec, Achitecture design and upgrade process defination | 4
Development ane environment setup and Knowlade on platform | 2
MSU state machine | 3
SCM Logic | 2
CCM Logic | 2
MSU Device Descovery | 2
MSU command handler | 2
MSU Encode/Decode feature | 1
MSU Error handler | 1
Abstraction and interfaces(TCP Stack and File system, Rtos) Wrok to fit into M80 architecture | 3
Project Management and Documentation | 1
Uint testing | 3
varification | 4
validation | 4
Total Effort | 34
MM | 8.5

## Server
Graphic User Interface
Offline Screens
|  | 1. Genera Netwrok - Configuration screen | 0.5
|  | 2. Range Detection Parameters | 0.5
|  | 3. Device Discovery | 1
|  | 4. IP Filtering | 0.5
|  | 5. Group Selection and Configuration | 1
|  | 6. File validation and Configuration | 1
|  | 7. Parameter Configuration | 0.5
|  | 8. Group Configuration for Multicast IP listing | 0.5
|  | 9. Transmission configuration with respect to RPI | 0.5
|  | 10. Network Self test | 0.5
|  | 11. Network filtering and time calculation | 1
|  | 12. General Configuration | 0.5
|  | 13. Log Message | 0.25
|  | 14. About | 0.25
|  | 15. Errors, notification and miscellaneous | 1
|  | 16. Help files | 0.25
| Sub Total |  | 9.75
Online Screens
|  | 1. Handshaking | 1
|  | 2. Group File transfer | 0.5
|  | 3. Online data Status and Log message | 0.25
|  | 4. Diagnostics | 0.5
|  | 5. Device Upload | 1
|  | 6. Device Download | 1
| Sub Total |  | 4.25
Business Logic
|  | 1. Socket class | 0.5
|  | 2. Task and event creation | 0.5
|  | 3.. MSU protocol | 8
|  | 4. Priority class | 0.25
|  | 5. Data buffer and bucket concepts | 0.25
|  | 6. Memory handling | 0.25
|  | 7. DMA concept in kernel for accessing more chunk of data (if required can move to win kernel using Windows driver model WDM) | 0.25
|  | 8. Data management (pool buffer concept) | 0.25
|  | 9. trace logs and exceptions management | 0.25
| Sub Total |  | 10.5
COM interface
1. UI to business logic
Others
1. UI design - .net
2. Business logic (oops)
|  | 3. testing, optimization | 4
|  | Verificarion | 4
|  | Validation | 4
| Sub Total |  | 12
| Total |  | 36.5
| MM |  | 9.125

## Server_breakup
MSU Server Development Effort
MSU Server Activity | Effort in week
Product spec, Achitecture design and upgrade process defination | 4
Data Display logic and Screen | 4
MSU data processing | 2 |  | MSU state machine | 4
MSU Error handler | 1 |  | SCM Logic | 2
Abstraction and interfaces(TCP Stack and File system) | 1 |  | CCM Logic | 2
Project Management and quality Documentation | 1
buffer | 2
Uint testing | 4
varification | 4
validation | 4
Total Effort | 27
MM | 6.75
MSU Server (PC Development) | MSU Client (IPCL FW) | Deployment On Mx80
5MM Dev | 4MM Dev | 1MM porting+ Uint testing
1 MM Integration test | 1 MM Integration test
.25 Field Test | .25 Field Test