## MSU Client Application
MSU Client Application - Product Backlog
Task ID | Main Task Backlog | Sub Task ID | Sub Task Backlog | Micro Task ID | Micro Level Tasks | Estimate (Hrs) | Task Type | Resource
MSU_1 | Design Document | [5 empty] | Start
|  | MSU_1.1 | SDS - Software Design Specification |  |  | 30 | Seq1 | Amulya/Senthil
|  | MSU_1.2 | DDS - Detailed Design Specification |  |  | 50 | Seq2 | Amulya/Senthil
MSU_2 | Who-Is | [5 empty] | Seq3
|  | MSU_2.1 | Modification and test |  |  | 24 | Parallel1 | Senthil
MSU_3 | Authentication
|  | MSU_3.1 | Frame format definition |  |  | 8 | Parallel1 | Amulya Done
|  | MSU_3.2 | Specification Update |  |  | 8 | Parallel1 | Amulya Done
Seq4
|  | MSU_3.3 | Firmware Implementation |  |  | 16 | Parallel2 | Senthil
|  | MSU_3.4 | Encryption and decryption |  |  | 40 | SeqA | Senthil
|  | MSU_3.5 | Integration testing with Server |  |  | 8 | SeqB | Senthil
|  | MSU_3.6 | code review |  |  | 8 | SeqC | Pawan/Deepak
|  | MSU_3.7 | Verification & Changes |  |  | 16 | SeqD | Senthil
MSU_4 | Group Creation
|  | MSU_4.1 | Modify frame format with network ID |  |  | 8 | Parallel2 | Amulya
|  | MSU_4.2 | Firmware Implementation |  |  | 24 | SeqA | Amulya
|  | MSU_4.3 | code review |  |  | 8 | SeqB | Amulya
|  | MSU_4.4 | Integration testing with Server |  |  | 8 | SeqC | Amulya
|  | MSU_4.5 | Verification & Changes |  |  | 16 | SeqD | Amulya
MSU_5 | Notification Message | [5 empty] | Seq5
|  | MSU_5.1 | Encrypting transaction ID |  |  | 40 | Parallel3 | Amulya
|  | MSU_5.2 | code review |  |  | 8 | SeqA | Pawan/Deepak
|  | MSU_5.3 | Verification and changes |  |  | 16 | SeqB | Amulya
MSU_7 | Flash/RAM storage | [5 empty] | Seq6
|  | MSU_6.1 | Implementation and Testing for Flash/RAM storage |  |  | 80 | Parallel4 | Amulya
|  | MSU_6.2 | code reivew |  |  | 8 | SeqA | Pawan/Deepak
|  | MSU_6.3 | verification and change |  |  | 16 | SeqB | Amulya
MSU_6 | Library with API | [5 empty] | Seq5
|  | MSU_7.1 | Linux Simulator |  |  | 120 | Parallel3 | Senthil
|  | MSU_7.2 | Integration testing |  |  | 40 | SeqA | Senthil
|  | MSU_7.3 | code reivew |  |  | 16 | SeqB | Pawan/Deepak
|  | MSU_7.4 | code change |  |  | 8 | SeqC | Senthil
|  | MSU_7.5 | TeSysT Porting |  |  | 8 | SeqD | Senthil
[6 empty] | 632 | Man Hours
[6 empty] | 79 | Man Days
[6 empty] | 3.4348 | Man Months